| Leadership Policy Paper Staff Leadership |  |
| --- | --- |

| Title | Mentors in Violence Prevention |
| --- | --- |
| Link to school vision and values and UNCRC | Show Kindness to Belong – Article 2 – The right to not be discriminated against due to ethnicity, sex, religion, language, abilities, or any other status, whatever they think or say, whatever their family background Contribute to Grow – Article 29 – The right to an education which develops the personality, talents and abilities of young people |
| Link to How Good is our School 4 Quality Indicators | 2.1 Safeguarding and child protection The ethos and vision of the school strongly promotes equality, challenging all forms of discrimination. 3.1 Ensuring wellbeing, equality and inclusion Learners, parents and carers, staff and partners feel that they are treated with respect and in a fair and just manner. We understand, value and celebrate diversity and challenge discrimination. |
| Strategic Lead | Emma Ferguson |
| Date | June 2026 |
| Vision | - Increased understanding of power in relationships, misogynistic vocabulary and behaviour that has negative impacts. - Improved awareness and prevention of violence against women and girls. |
| Outcome Statement 2024-25 What? How? When? Who? | - For senior pupils to be MVP trained and deliver the peer-education programme to S1 and S2 young people. June-October - Deliver MVP Core Sessions to S5 in June (EF, NH, GC, EW) - Complete pre mentor training survey. Deliver training session to MVP volunteers (EF, NH, GC, EW + Viv Carsley). - Form senior groups and agree times to deliver 2 sessions to S1 + S2 classes. - Complete pre-mentee survey with S1 + S2 classes. - Begin delivering sessions November-December - Continue delivering classes - Complete post-mentee survey with S1 + S2 classes after delivery - Complete post-mentor survey - EF to complete School Leader survey and send to local authority lead. Input from NH, GC and EW. January-June - EF to collate mentor and mentee surveys and send to local and national leads. - Deliver Everyone Included to P7 during transition visit. |
| Parent/Carer input | - Parent Council – MVPs to share information about the programme with the Parent Council. This could be in person on by a pre-prepared video. |
| Pupil input | - Senior students to deliver MVP to S1 and S2 students - Feedback from S1, S2 and MVPs via quality assurance questionnaires. |
| Next Steps 2027-28 | - Measure impact of MVP - Consider feedback from surveys and make appropriate changes |