| Leadership Policy Paper – Parental Engagement | One Peebles: our community where we belong, grow and achieve. | Work hard Show kindness Contribute |
| --- | --- | --- |

| Title | Parental Engagement |
| --- | --- |
| Quality Indicators from HGIOS 4 | 1.3 Leadership of Change |
| Strategic Lead | Neil Hattie |
| Date | October 2025 |
| Vision | Parents and carers will - Believe that communication between school and families regarding key dates and information is improved. - Believe that they know where to find resources to support learning at home |
| Outcome Statement 2024-25 | Outcome 1 – PHS Learning Hub Ensure that all home learning resources are collated, organised and stored on a dedicated section of the PHS website. Outcome 2 – Identifying “Key Information” Work with staff and parents to streamline the information going home. Ensuring parents receive key information about assessments, homework deadlines and course information. Outcome 3 – Singular Communication Platform Ensure that staff are communicating the agreed information through the same platform via group call. |
| What? How? When? Who? | Short-Term (Oct-Dec) - Begin discussions with staff/parents and staff working group about what is classified as key information that needs to be communicated via group call. - Begin auditing current PHS website and identifying good practice in terms of home learning resources. Work with K. Smith to create PHS Home Learning Hub. - Discuss planned changes with staff and gather feedback. ASM/INSET time possibly required. Medium-Term (January – End of Session) - Implement new communication practices with focus on Senior Phase. - Focus especially on SQA coursework assignments, and also important summative assessments. - Launch and publicise new PHS Home Learning Hub. - Continue to add new resources for supporting learners to Home Learning Hub. Long-Term (Summer Term) - Evaluate and monitor improvements through re-surveying of parents, especially focusing on Q18 of HMIe survey. |
| Parent/Carer input | Extensive survey of parental opinion has been carried out, looking to identify what parents/carers want from the school to be able to better support learners at home. Survey identified three clear priorities. 1. More communication of key deadlines (85%) 2. Departments using the subject platform to communicate (80%) 3. Communicating expectations in certificated subjects, course outlines and key dates. (69%) 4. Central PHS Hub for learning resources. (61%) Presentation and discussion at Parent Council where broad support was secured for the aims of this project. An understanding that while progress has been made, there is more to do. |
| Pupil input | Organise discussions with Student Parliament to establish what they feel is needed to help them work more effectively at home and in tandem with their parents/carers. |
| Next Steps 2025-26 | - Implement new communication strategies - Begin preparations for new PHS Home Learning Hub - Continue to engage with stakeholders and monitor improvements. |