| Leadership Policy Paper S6 QS Leadership Award June 2026 |  |
| --- | --- |

| Title | S6 QS Leadership Award |
| --- | --- |
| Link to school vision and values and UNCRC | Work Hard to Achieve – Article 28 – The right to an education |
| Link to How Good is our School 4 Quality Indicators | 3.2 raising attainment and achievement |
| Strategic Lead | Alastair Scott, Principal Teacher of Pupil Support (Pastoral) |
| Date | June 2026 |
| Vision | To provide all S6 students with meaningful opportunities to develop and demonstrate leadership skills, building their confidence, teamwork, communication and resilience through the planning and delivery of leadership activities and events that positively contribute to the school community. |
| Outcome Statement 2026-27 What? How? When? Who? | By May 2027 the current S6 year group will have completed and gained their QS Level 5 award in Leadership. June 2026 - A.Scott to present to S6 Induction Day outlining course purpose and course outline. - Creation of S6 Leadership Teams for sharing resources of powerpoints, worksheets and communications. - In June S6 will have two periods a week of Leadership Lessons. - All of S6 will be taught by A.Scott unit 1 Leadership in Practice unit. This will allow 8 periods of lessons and allow time for all of S6 to then complete their Unit 1 Leaderhsip report. - Organisation of Teachers to present their groups to the S6 cohort and S6 will sign up to their preferred Leadership groups for before August. - A.Scott to organise and assign class registers and liase with office staff for creation of classes onto Seemis. - A.Scott to receive QS Verification report and implement suggested changes. August 2026 In August inset day A.Scott to meet with teaching staff to outline QS Assessment materials, resources, course outline and Internal Verification Calendar. - A.Scott to create Moderation Calendar to take samples of pupils work for Internal Verification. - Creating of a attendance spreadsheet for A.Scott to share with PSAs for calls/letters home for attendance. September – December 2026 - Focus on Unit 2 of Leadership in Practice and collecting of evidence for pupils. - Meeting 2 with teaching staff for progress update and Internal Verification review. - Creation of a timetable calendar and application form to be approved by SLT 5 weeks in advance. - Organising of speakers to come into the school to speak about personal leadership experiences. January – March 2027 - Majority of pupils should have completed with their leadership projects. Final tracking and monitoring meetings with staff and IV meetings. - Input of tracking data for completion of course and units into Seemis. |
| Parent/Carer input | Parental Communication home. |
| Pupil input | Evaluation Forms from Pupils and allowing pupils to pick their groups and events. |
| Next Steps 2026-27 | Continued Development of new S6 leadership groups and increasing number of S6 achieving leadership award. |