| Leadership Policy Paper Senior Volunteering (SWAG) June 2026 |  |
| --- | --- |

| Title | Senior Volunteering (SWAG ???) |
| --- | --- |
| Link to school vision and values and UNCRC | Contribute to Grow – Article 29 – The right to an education which develops the personality, talents and abilities of young people |
| Link to How Good is our School 4 Quality Indicators | 3.2 raising attainment and achievement 3.1 Ensuring wellbeing, equality and inclusion |
| Strategic Lead | Alastair Scott, Principal Teacher of Pupil Support (Pastoral) |
| Date | June 2026 |
| Vision | To engage all S5 and S6 pupils in meaningful volunteering opportunities that develop confidence, leadership and employability skills, enabling them to become effective contributors within their school and local community. Through participation in volunteering activities, pupils will also have opportunities to build and achieve Saltire Award hours, recognising and celebrating their contribution to others. |
| Outcome Statement 2026-27 What? How? When? Who? | S5/6 pupils will undertake meaningful volunteering opportunities within school or the local community. Through these experiences, pupils will develop confidence, teamwork, communication and leadership skills while making a positive contribution to others. August 2026 - Communication with local community partners, charities and school-based volunteering groups to invite participation in the PHS Volunteering Fayre. - Liaison with partners to gather information on volunteering opportunities, duties and responsibilities available to pupils. - Creation and publication of the PHS SWAG (Student Volunteering and Achievement Guide) booklet outlining volunteering opportunities, Saltire Awards and the benefits of volunteering. September 2026 - Delivery of PSE inputs to S3–S6 pupils promoting volunteering opportunities and the Saltire Awards programme. - Organisation and delivery of the PHS Volunteering Fayre, enabling pupils to engage directly with community partners and learn about available volunteering opportunities. - Implementation of QR code sign-up systems to allow pupils to register interest in volunteering opportunities and community projects. - Registration of interested pupils for the Saltire Awards programme. October 2026 – March 2027 - Pupils to participate in volunteering opportunities within school and the wider community. - Ongoing collection and recording of Saltire Award hours and evidence of volunteering. - Regular communication with community partners to monitor opportunities and pupil engagement. - Organisation of assemblies, workshops and PSE inputs from community partners to highlight the impact and value of volunteering. - Celebration and promotion of pupil achievements through assemblies, social media, newsletters and award presentations. April – June 2027 - Review of pupil participation rates, Saltire Award achievements and community partnerships. - Evaluation of the impact of volunteering on pupil confidence, teamwork, leadership and employability skills. - Identification of priorities and opportunities for further development during session 2027–28. |
| Parent/Carer input | Parental Communication home. |
| Pupil input | Evaluation Forms from Pupils and allowing pupils to pick their volunteering group. |
| Next Steps 2026-27 | - Continued Development of SWAG Booklet. - Look at exploring expanding programme to S4 and 5. |