| Leadership Policy Paper Digital Strategy and Digital Schools Award June 2026 |  |
| --- | --- |

| Title | Developing a Whole-School Digital Strategy through Learner Leadership and the Digital Schools Award |
| --- | --- |
| Link to school vision and values and UNCRC | Vision and values: Work hard to achieve, show kindness to belong, contribute to grow. UNCRC Articles 12, 13, 17 & 29. |
| Link to How Good is our School 4 Quality Indicators | 1.3 Leadership of Change - Develops a shared vision for digital improvement through effective collaboration with learners. - Uses robust self-evaluation and evidence to identify priorities for improvement. - Promotes leadership at all levels, empowering young people to lead meaningful change. 2.2 Curriculum - Ensures learners develop the digital skills, knowledge and attributes required for learning, life and work. - Designs an inclusive curriculum which reflects the increasing importance of digital literacy and digital citizenship. 2.3 Learning, Teaching and Assessment - Digital technologies are used effectively to enhance learning, teaching and assessment. - Learners confidently use digital technologies to collaborate, create and communicate. 2.7 Partnerships - Develops strong partnerships with learners, families and the wider community to improve outcomes. - Young people are genuine partners in planning, evaluating and improving school practice. 3.1 Ensuring Wellbeing, Equality and Inclusion - Learners feel listened to and know that their views influence change. - Digital systems promote equity, accessibility and effective communication for all learners. |
| Strategic Lead | Karen Mooney (DHT) |
| Date | June 2026 |
| Vision | To develop a whole-school Digital Strategy in partnership with the Student Parliament that enhances learning, teaching, communication and participation. Pupils will lead digital improvement, coordinate evidence for the Digital Schools Award and shape the future digital culture of the school. |
| Outcome Statement 2026-27 What? How? When? Who? | Outcome Statements: • Whole-school Digital Strategy co-created with Student Parliament. • Student Digital Leaders coordinate evidence for the Digital Schools Award. • Digital display screens, SharePoint and Year Group Team communication reviewed and improved. • Learner voice drives digital improvement. Actions: Aug–Sept: Establish Digital Strategy Group; audit against Digital Schools Award. Oct–Dec: Draft strategy; pupil consultation; review communication. Jan–Mar: Implement improvements; gather evidence. Apr–May: Complete award submission. June: Evaluate impact. |
| Parent/Carer input | • Parent consultation through surveys on digital communication. • Feedback informs Digital Strategy priorities and Digital Schools Award evidence. |
| Pupil input | • Student Parliament co-leads the Digital Strategy. • Gather evidence for the Digital Schools Award. • Manage digital display screens. • Develop pupil SharePoint. • Review Year Group Team communication. • Lead pupil consultation and report to SLT. |